## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Diagram not correct | 2 | 10 | 20 | 2021-04-02 | Mitigated | M | Talked with professor about diagram
Accidentilly delete project planning doc | 1 | 30 | 30 | 2021-04-02 | Mitagated | M | I will save my doc a lot so I do not lose much even if my computer crashes
The Physics requires Diff-eq | 5 | 100 | 500 | 2021-04-08 | Mitigated | M | Proffessor said it wasn't required
Not certain on if write up is correct | 20 | 100 | 2000 | 2021-04-09 | Accepted | A | Already turned in week 1 about to turn in week 2
Redo physics Unit Test | 70 | 5 | 350 | 2021-04-09 | Accepted | A | hard to know if physics unit test will work when we haven't created the physics function yet
Writing Physics Equations | 70 | 40 | 2800 | 2021-04-09 | Owned | O | We do not have the equations finalized so we don't have a solution yet
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100