## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Diagram not correct | 2 | 10 | 20 | 2021-04-02 | Mitigated | M | Talked with professor about diagram
Accidentilly delete project planning doc | 1 | 30 | 30 | 2021-04-02 | Mitagated | M | I will save my doc a lot so I do not lose much even if my computer crashes
The Physics requires Diff-eq | 1 | 100 | 100 | 2021-04-08 | Mitigated | M | Proffessor said it wasn't required
Not certain on if write up is correct | 1 | 70 | 70 | 2021-04-09 | Resolved | R | Got good grade on week 1 and 2 so this is no longer a risk
Redo physics Unit Test | 20 | 1 | 20 | 2021-04-09 | Resolved | R | Physics Unit Tests are complete
Writing Physics Equations | 25 | 1 | 25 | 2021-04-09 | Resolved | R | Equations still are finalized
LCD has caused others problems | 30 | 40 | 1200 | 2021-04-16 | Accepted | A | We have the LCD is turning on and printing things but is not yet fully working
Speed of game | 20 | 5 | 100 | 2021-04-16 | Accepted | A | The game might be hard to play due to speed but as long as the physics work it should still give me a good grade
Message Queue | 40 | 40 | 1600 | 2021-04-23 | Accepted | A | The Message Queue may not work as expected and may need to find another way to communicate with the LCD task
0
0
0
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100